## Sheet1
UNIFORM STATUS OF FUNDS SPREADSHEET FOR: DATE: |  |  |  | "Anywhere Water and Sewer District" (EXAMPLE OF A COMPLETED SPREADSHEET) | [8 empty] | 2018-11-14 11:22
| Funding Source: TSEP |  |  |  | Funding Source: RD Grant |  |  |  | Funding Source: RD Loan |  |  |  | Total Budget
ADMINISTRATIVE/ FINANCIAL COSTS: | Budgeted | Previously Expended | Amount of Draw | Balance Remaining | Budgeted | Previously Expended | Amount of Draw | Balance Remaining | Budgeted | Previously Expended | Amount of Draw | Balance Remaining | Budgeted | Expended | Balance
Personnel Costs | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 500
Office Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Professional Services | 20000 | 7000 | 3000 | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 4000 | 6000 | 30000 | 14000 | 16000
Legal Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Audit Fees | 500 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 500
Travel & Training | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 40000 | 40000 | 0 | 40000
Loan Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 230000 | 0 | 0 | 230000 | 230000 | 0 | 230000
Loan Reserves | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Interim Interest | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bond Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
Total Administrative Costs | 21000 | 7000 | 3000 | 11000 | 0 | 0 | 0 | 0 | 280000 | 0 | 4000 | 276000 | 301000 | 14000 | 287000
ACTIVITY COSTS:
Land Acquisition | 22000 | 15000 | 0 | 7000 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 10000 | 32000 | 15000 | 17000
Preliminary Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Final Engineering Design | 20000 | 10000 | 5000 | 5000 | 0 | 0 | 0 | 0 | 20000 | 5000 | 7000 | 8000 | 40000 | 27000 | 13000
Construction Engineering | 15500 | 0 | 0 | 15500 | 50000 | 0 | 0 | 50000 | 200000 | 0 | 0 | 200000 | 265500 | 0 | 265500
Construction | 383500 | 0 | 0 | 383500 | 600000 | 0 | 0 | 600000 | 1700000 | 0 | 0 | 1700000 | 2683500 | 0 | 2683500
|  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
Contingency | 38000 |  |  | 38000 | 60000 |  |  | 60000 | 170000 |  |  | 170000 | 268000 | 0 | 268000
Total Activity Costs | 479000 | 25000 | 5000 | 449000 | 710000 | 0 | 0 | 710000 | 2100000 | 5000 | 7000 | 2088000 | 3289000 | 42000 | 3247000
TOTAL PROJECT COSTS | 500000 | 32000 | 8000 | 460000 | 710000 | 0 | 0 | 710000 | 2380000 | 5000 | 11000 | 2364000 | 3590000 | 56000 | 3534000
Copy and submit to the applicable funding agency with each drawdown request.
l:\cdbg\projmgt\new\fund.exmpl
Montana Department of Commerce CDBG / NSP Grant Administration Manual
2018
4-D.3
UNIFORM STATUS OF FUNDS SPREADSHEET FOR: DATE: